## Slide 1: @talentia/components
May 2020 Project Status
Gianluca Maggio

## Slide 2
Project footprint
Actual constraints:
  FE Framework is delivered as a Web Application connected to backend
  FE Framework is compound of:
    An Angular Application (Client)
    A Server Web Application (MVC) for serving Client and REST API
    A Server Engine for generating dynamic pages (json->angular)
    WCF Providers for connecting to BE services
  Components are part of the Framework Angular Application (Client)
Goal: reuse as much as possible Front-End Framework in a new Angular Application by creating one or more angular libraries
Project milestones:
  Phase 1 (“make it working”)
  Phase 2 (“make it ergonomic and easy to use”)
  Phase 3 (“refine and optimize”)

## Slide 3
Phase 1 – « make it working »
Isolation of base components (6 components) - done
Isolation of library components (89 components/subcomponents) - done
Isolation of 21 general purpose services - done
Abstraction of context services (translations, locale, formats) - done
Isolation of Shell components (10 components) – in progress (80%)
Isolation of Style System (theming based on bootstrap) – done
Build, Watch & Publish procedures - done
Schematics for adding the library and deps to new projects – in progress
  ng add @talentia/components
    dep: Libraries
    dep: Scripts
    dep: CSS
Output: alpha version published on npm

## Slide 4
Phase 2 - « Ergonomic & easy to use »
Online documentation (document & discover)
  Wiki (markdown)
  Feature by Example (a part is already available in the demo application)
  Links to reference (typedoc generated)
  Improve code comments for typedoc generation
Pass 2 refactoring
  Refactoring of not ergonimic components (for example chosen)
  Refactoring based on user voice
  Creation of new Components in library (splitter, dropdown tree-view, input with arrow)
Output: beta version published on npm

## Slide 5
Phase 3 – Refine and Optimize
Optimization of bundle and dependencies (i.e. moment vs date-fns)
Removing global object dependencies (browser window, resize, scroll)
Reducing non Angular native dependencies (jQuery dependencies)
Output: stable version published on npm

## Slide 6
Project planning
Expected release and effort
  Phase 1 – 15th may (3 FTE)
  Phase 2 – Progressive (1 FTE) from 18th May to 15th June
  Phase 3 – Continuous improvement until and after release
Branching/Release:
  Stable release will be included in Front-End Framework Release 1.5.
  Previews will be available after phase 1 on npm (private packages)